HeadlessResto

Development Task List

Version 1.0  |  March 2026

Tasks are organized into 6 phases. Each phase is a vertical slice of functionality that can be demoed end-to-end. Estimates assume a 2-person engineering team.

# Phase 1: Foundation & Auth (Weeks 1–2)

Establish the monorepo, Supabase project, CI/CD pipeline, and full authentication flow.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Init monorepo: apps/web, packages/ui, packages/types | FE | 4h | P0 |
| Configure Next.js 14 App Router + TypeScript + Tailwind | FE | 3h | P0 |
| Set up Supabase project (prod + staging) | BE | 2h | P0 |
| Define initial DB schema + migrations (restaurants, users, locations) | BE | 6h | P0 |
| Implement RLS policies for multi-tenancy | BE | 8h | P0 |
| JWT custom claims hook (role, restaurant_id, location_id) | BE | 4h | P0 |
| Auth pages: Login, Signup, Forgot Password | FE | 6h | P0 |
| Next.js middleware for role-based route protection | FE | 4h | P0 |
| GitHub Actions: type check, lint, migration validation on PR | DevOps | 4h | P0 |
| Vercel deployment setup (prod + staging + preview) | DevOps | 2h | P0 |
| Shared UI library: Button, Input, Card, Badge, Toast | FE | 8h | P0 |

# Phase 2: Onboarding & Admin Dashboard (Weeks 3–4)

Self-serve signup, Super Admin panel, multi-location setup, and staff management.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Self-serve onboarding wizard (restaurant details, location, timezone) | FE | 10h | P0 |
| Stripe Connect onboarding integration | BE | 8h | P0 |
| Super Admin dashboard: tenant list, create/suspend restaurant | FE | 10h | P0 |
| Super Admin: impersonate any restaurant admin | BE | 6h | P0 |
| Restaurant Admin dashboard layout (sidebar nav) | FE | 6h | P0 |
| Multi-location management: add/edit/deactivate locations | FE | 8h | P1 |
| Staff management: invite, assign role, assign location | FE | 10h | P0 |
| Shift scheduler: weekly view, drag-and-drop, publish | FE | 16h | P1 |
| Payslip generation: compute from shifts + hourly rate | BE | 8h | P1 |
| Payslip PDF generation + email dispatch | BE | 6h | P1 |

# Phase 3: Menu & QR Ordering (Weeks 5–6)

Menu builder, QR code generation, and customer-facing ordering flow.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Menu builder: categories, items, variants, images (Supabase Storage) | FE | 16h | P0 |
| Location menu overrides (inherit vs custom per location) | BE | 6h | P1 |
| Table management + QR code generation per table | FE | 8h | P0 |
| QR menu PWA: category browsing, item detail, variant selection | FE | 20h | P0 |
| Cart management + order placement API | BE | 8h | P0 |
| Dine-in flow: QR → table detection → order → send to kitchen | FE | 10h | P0 |
| Takeaway flow: QR / link → order → estimated pickup time | FE | 8h | P0 |
| Service Worker: offline menu cache via Workbox | FE | 8h | P1 |
| Real-time item availability (mark out-of-stock from admin) | BE | 4h | P1 |

# Phase 4: KDS & POS (Weeks 7–8)

Kitchen Display System and Cashier Point of Sale, including offline support.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| KDS layout: order cards grid, status columns | FE | 12h | P0 |
| Supabase Realtime: subscribe to orders:{location_id} | BE | 6h | P0 |
| KDS: bump, hold, flag item actions | FE | 6h | P0 |
| KDS: audio alert on new order | FE | 2h | P1 |
| KDS PWA + dark mode + fullscreen mode | FE | 4h | P1 |
| IndexedDB schema setup (Dexie.js) | FE | 6h | P0 |
| KDS offline: queue orders locally, sync on reconnect | FE | 10h | P0 |
| POS layout: menu grid + order summary panel | FE | 14h | P0 |
| POS: manual order creation, quantity, discounts | FE | 8h | P0 |
| POS offline: cash order queue, card order defer | FE | 10h | P0 |
| /api/sync endpoint: batch offline queue processing | BE | 10h | P0 |
| Waiter app: table selection, item ordering, notes | FE | 12h | P0 |
| Waiter app offline support | FE | 8h | P0 |

# Phase 5: Payments & Delivery (Weeks 9–10)

Stripe payment flows and Uber Direct delivery integration.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Stripe Checkout: QR menu customer self-pay flow | BE | 8h | P0 |
| Stripe Terminal SDK: POS card-present payments | FE | 12h | P0 |
| Split bill logic in POS | FE | 8h | P1 |
| /api/webhooks/stripe: payment confirmation, refund handling | BE | 8h | P0 |
| Digital receipt: email via Supabase Edge Function | BE | 4h | P1 |
| Delivery flow UI: address input, dispatch button in POS/admin | FE | 8h | P0 |
| /api/delivery/create: Uber Direct job dispatch | BE | 8h | P0 |
| /api/webhooks/uber: status updates to order record | BE | 6h | P0 |
| Customer delivery tracking page (link from receipt) | FE | 6h | P1 |
| Uber Direct QR menu delivery flow (address at checkout) | FE | 8h | P1 |

# Phase 6: Reports, Polish & Launch Prep (Weeks 11–12)

Analytics, reporting, accessibility audit, and production hardening.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Restaurant admin: daily/weekly sales report | FE | 10h | P1 |
| Cross-location analytics for restaurant admin | FE | 8h | P1 |
| Super Admin platform analytics (MRR, active tenants, orders) | FE | 10h | P1 |
| WCAG 2.1 AA audit on QR menu (screen reader, contrast) | FE | 8h | P1 |
| Load testing: simulate 100 concurrent orders on KDS | BE | 6h | P1 |
| Security audit: RLS policy review, API auth headers | BE | 6h | P0 |
| Error monitoring setup (Sentry) | DevOps | 4h | P0 |
| Supabase backup + PITR verification | DevOps | 2h | P0 |
| End-to-end test suite (Playwright): critical order flows | FE | 16h | P1 |
| Documentation: API docs, onboarding guide, staff training | Both | 12h | P1 |
| Soft launch: onboard 2–3 pilot restaurants | Both | Ongoing | P0 |

# Summary

| Phase | Duration | Est. Hours | Focus |
| --- | --- | --- | --- |
| Phase 1: Foundation & Auth | Weeks 1–2 | ~51h | Infrastructure |
| Phase 2: Admin & Staff | Weeks 3–4 | ~88h | Operations |
| Phase 3: Menu & QR | Weeks 5–6 | ~88h | Customer |
| Phase 4: KDS & POS | Weeks 7–8 | ~108h | Operations |
| Phase 5: Payments & Delivery | Weeks 9–10 | ~76h | Revenue |
| Phase 6: Polish & Launch | Weeks 11–12 | ~82h | Quality |
| Total | 12 Weeks | ~493h |  |